## Sheet1
| Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16
LO1
Design | bar: Week2 to Week4
Development | bar: Week5 to Week16
Testing | bar: Week5 to Week16
Webpages | bar: Week5 to Week16
Presentation | bar: Week5 to Week6; Week10
Sitemap
Project Plan
Evaluation Strategy
Testing Strategy
October Holidays | bar: Week8